## Task_Table
ID | Title | Start | Finish | Predecessors | Notes
1 | South Tacoma (STSAI) Phase 2 NTP | 2022-05-02 | 2022-05-02 08:00 |  | Scheduled
2 | Phase 2 complete | 2024-02-07 | 2024-02-07 | 11,12,13,14,17,160,120,183,271,53,117,159,158,8,107,269,23,20,21,22,16,182,263,192,10,255,175
3 | 1 Project Management, Controls and QA | 2022-05-02 | 2023-09-29
4 | 1.1 Project Management Plan | 2022-05-02 | 2022-06-17
5 | Draft P | 2022-05-02 | 2022-05-13 | 1
6 | QAQC Draft P | 2022-05-16 | 2022-05-20 | 5
7 | ST review P | 2022-05-23 | 2022-06-03 | 6
8 | Update Final P | 2022-06-06 | 2022-06-10 | 7
9 | QAQC Final P | 2022-06-13 | 2022-06-17 | 8
10 | Submit Final P | 2022-06-17 | 2022-06-17 | 9
11 | 1.2 Scheduling | 2022-05-02 | 2023-09-29 | 1
12 | 1.3 Contract Admin/Progress Reports/Invoicing | 2022-05-02 | 2023-09-29 | 1
13 | 1.4 Project Management Te Meetings | 2022-05-02 | 2023-09-29 | 1
14 | 1.5 Progress Reports | 2022-05-02 | 2023-09-29 | 1
15 | 1.7 Phase 2 Quality Management | 2022-05-02 | 2023-09-29
16 | Quality Management Plan | 2022-05-02 | 2022-05-13 | 1
17 | Complete QC documentation for deliverables | 2022-05-02 | 2023-09-29 | 1
18 | 1.8 Safety and Security Certification | 2022-05-02 | 2023-09-29
19 | Meetings (2 per month) | 2022-05-02 | 2023-09-15 | 1
20 | Preliminary engineering initial PHA and PHA report | 2023-09-18 | 2023-09-29 | 19
21 | Project specific SSMP (draft) | 2023-09-18 | 2023-09-29 | 19
22 | Project specific CIL and verification matrix (excel) | 2023-09-18 | 2023-09-29 | 19
23 | Montly report | 2022-05-02 | 2023-09-15 | 1
24 | 2 Environmental Review | 2022-05-02 | 2024-01-26
25 | Environmental kick off | 2022-08-23 | 2022-08-23 | 1 | Scheduled
26 | 2.1 SEPA Checklist | 2022-08-24 | 2024-01-26
27 | Methodology Memos | 2022-08-24 | 2022-11-29
28 | Develop Methodology Memos - Draft 1 | 2022-08-24 | 2022-10-14 | 25 | Initially 10 days duration
29 | QAQC Methodology Memos - Draft 1 | 2022-10-17 | 2022-10-26 | 28 | Transpo in 10/24; Visual and EJ 10/27
30 | Develop Methodology Memos - ST Review | 2022-10-27 | 2022-11-10 | 29
31 | Develop Methodology Memos - Final | 2022-11-11 | 2022-11-22 | 30
32 | QAQC Methodology Memos - Final | 2022-11-23 | 2022-11-29 | 31
33 | Submit Methodology Memos - Final | 2022-11-29 | 2022-11-29 | 32
34 | Site Visit | 2022-10-19 | 2022-10-19 | 25
35 | SEPA Checklist | 2023-07-17 | 2024-01-26
36 | Develop SEPA checklist draft 1 for ST review | 2023-07-17 | 2023-08-25 | 34,33,234,73FF+20d,101FF+20d | CTR - 20 days FF
37 | QAQC SEPA checklist draft 1 | 2023-08-28 | 2023-09-08 | 36
38 | ST review SEPA check list draft 1 | 2023-09-11 | 2023-09-22 | 37
39 | Develop SEPA checklist draft 2 for ST review | 2023-09-25 | 2023-10-06 | 38
40 | QAQC SEPA checklist draft 2 | 2023-10-09 | 2023-10-13 | 39
41 | ST review SEPA check list draft 2 | 2023-10-16 | 2023-10-27 | 40
42 | Develop SEPA checklist draft 3 for ST review | 2023-10-30 | 2023-11-03 | 41,82,106,65,60
43 | QAQC SEPA checklist draft 3 | 2023-11-06 | 2023-11-10 | 42
44 | ST review SEPA check list draft 3 | 2023-11-13 | 2023-11-17 | 43
45 | Develop SEPA checklist draft 4 for ST legal review | 2023-11-20 | 2023-11-24 | 44
46 | QAQC SEPA checklist draft 4 | 2022-11-27 | 2023-12-01 | 45
47 | ST legal review SEPA check list draft 4 | 2023-12-04 | 2023-12-22 | 46
48 | Develop SEPA checklist print-check draft 5 for ST review | 2023-12-25 | 2023-12-29 | 47
49 | QAQC SEPA checklist draft 5 | 2024-01-01 | 2024-01-05 | 48
50 | ST review SEPA check list draft 5 | 2024-01-08 | 2024-01-12 | 49
51 | Finalize SEPA checklist | 2024-01-15 | 2024-01-19 | 50
52 | QAQC SEPA checklist final | 2024-01-22 | 2024-01-26 | 51
53 | Submit SEPA check list final | 2024-01-26 | 2024-01-26 | 52
54 | 2.2 Technical Reports | 2022-10-17 | 2023-10-24
55 | 2.2.1 Transportation Technical Report | 2023-03-23 | 2023-10-24
56 | Analysis | 2023-03-23 | 2023-05-17 | 204,33,206FF+20d | Unlinked noise
57 | Develop TTR - Draft 1 | 2023-05-18 | 2023-05-31 | 56 | Shorten duration as substantial text is written as of 4/10
58 | QAQC TTR - Draft 1 | 2023-06-01 | 2023-06-07 | 57
59 | ST review of Draft 1 of TTR | 2023-06-08 | 2023-06-21 | 58
60 | Develop TTR - Draft 2 | 2023-09-13 | 2023-09-26 | 59,209 | Linked to CE comment resolution due to changes in def
61 | QAQC TTR - Draft 2 | 2023-09-27 | 2023-10-03 | 60
62 | ST Review Draft 2 of TTR | 2023-10-04 | 2023-10-10 | 61
63 | Develop TTR - Final | 2023-10-11 | 2023-10-17 | 62
64 | QAQC TTR - Final | 2023-10-18 | 2023-10-24 | 63
65 | Submit TTR - Final | 2023-10-24 | 2023-10-24 | 64
66 | 2.2.2 Cultural Resources Technical Report | 2022-10-17 | 2023-09-20
67 | Develop APE | 2022-10-17 | 2022-10-28 | 1
68 | SHPO review and approve APE | 2022-10-31 | 2022-11-28 | 67
69 | Field Work | 2023-01-03 | 2023-01-20 | 68
70 | Cultural Resources Tech Report | 2023-06-01 | 2023-09-20
71 | Develop CRTR - Draft 1 | 2023-06-01 | 2023-06-28 | 69,33,207 | Link to methodology memos
72 | QAQC CRTR - Draft 1 | 2023-06-29 | 2023-07-05 | 71
73 | ST Review CRTR - Draft 1 | 2023-07-06 | 2023-07-19 | 72
74 | Develop CRTR - Draft 2 | 2023-07-20 | 2023-08-02 | 73
75 | QAQC CRTR - Draft 2 | 2023-08-03 | 2023-08-09 | 74
76 | ST Review CRTR - Draft 2 | 2023-08-10 | 2023-08-16 | 75
77 | Develop CRTR - Draft 3 | 2023-08-17 | 2023-08-23 | 76
78 | QAQC CRTR - Draft 3 | 2023-08-24 | 2023-08-30 | 77
79 | ST Review CRTR - Draft 3 | 2023-08-31 | 2023-09-06 | 78
80 | Develop CRTR - Final | 2023-09-07 | 2023-09-13 | 79
81 | QAQC CRTR - Final | 2023-09-14 | 2023-09-20 | 80
82 | Submit final CRTR | 2023-09-20 | 2023-09-20 | 81
83 | Historic Property Inventory Forms | 2023-05-25 | 2023-09-13
84 | Develop HPI - Draft 1 | 2023-05-25 | 2023-06-28 | 69,204,33,71FF | Unlink from schedule - combine with CR TR
85 | QAQC HPI - Draft 1 | 2023-06-29 | 2023-07-05 | 84
86 | ST Review HPI - Draft 1 | 2023-07-06 | 2023-07-12 | 85
87 | Develop HPI - Draft 2 | 2023-07-13 | 2023-07-26 | 86
88 | QAQC HPI - Draft 2 | 2023-07-27 | 2023-08-02 | 87
89 | ST Review HPI - Draft 2 | 2023-08-03 | 2023-08-09 | 88
90 | Develop HPI - Draft 3 | 2023-08-10 | 2023-08-16 | 89
91 | QAQC HPI - Draft 3 | 2023-08-17 | 2023-08-23 | 90
92 | ST Review HPI - Draft 3 | 2023-08-24 | 2023-08-30 | 91
93 | Final HPI | 2023-08-31 | 2023-09-06 | 92
94 | QAQC Final HPI | 2023-09-07 | 2023-09-13 | 93
95 | Submit Final HPI | 2023-09-13 | 2023-09-13 | 94 | Unlink from schedule - combine with CR TR
96 | 2.2.3 Noise Technical Memorandum | 2023-06-01 | 2023-08-25
97 | Analysis | 2023-06-01 | 2023-06-21 | 207
98 | Develop NTR - Draft 1 | 2023-06-22 | 2023-06-28 | 97
99 | QAQC NTR - Draft 1 | 2023-06-29 | 2023-07-05 | 98
100 | ST Review NTR - Draft 1 | 2023-07-06 | 2023-07-21 | 99
101 | Develop NTR - Draft 2 | 2023-07-24 | 2023-07-28 | 100
102 | QAQC NTR - Draft 2 | 2023-07-31 | 2023-08-04 | 101
103 | ST Review NTR - Draft 2 | 2023-08-07 | 2023-08-11 | 102
104 | Develop Final NTR | 2023-08-14 | 2023-08-18 | 103
105 | QAQC Final NTR | 2023-08-21 | 2023-08-25 | 104
106 | Submit Final NTR | 2023-08-25 | 2023-08-25 | 105
107 | 2.3 Environmental Te Meetings | 2022-05-02 | 2023-09-29 | 1
108 | 3 Stakeholder Involvement | 2022-05-02 | 2024-02-07
109 | Outreach planning workshop | 2022-05-18 | 2022-05-18 | 1
110 | 3.1 Public Involvement Plan | 2022-05-19 | 2022-07-27
111 | Draft PIP | 2022-05-19 | 2022-06-15 | 109
112 | QAQC Draft PIP | 2022-06-16 | 2022-06-22 | 111
113 | ST review PIP | 2022-06-23 | 2022-07-06 | 112
114 | Final PIP | 2022-07-07 | 2022-07-20 | 113
115 | QAQC Final PIP | 2022-07-21 | 2022-07-27 | 114
116 | Submit Final PIP | 2022-07-27 | 2022-07-27 | 115
117 | 3.2 Public Involvement Task Management | 2022-05-02 | 2023-09-29 | 1
118 | 3.3 Technical Advisory Group Meetings | 2022-05-02 | 2023-09-22
119 | TAG #1 - KO | 2022-05-20 | 2022-05-20 | 1
120 | TAG #2-8 | 2022-05-23 | 2023-09-22 | 119
121 | TAG - Prep OOH | 2022-05-02 | 2022-05-02
122 | TAG - Report out on OOH, design decisions | 2022-05-02 | 2022-05-02
123 | 3.4 Online and In-Person Public Engagement | 2022-07-28 | 2023-12-13
124 | Focused area outreach (round 1) - South Tacoma | 2022-07-28 | 2022-12-19
125 | T approve approach | 2022-07-28 | 2022-07-28 08:00
126 | South Tacoma review approach | 2022-08-22 | 2022-08-22 08:00
127 | Content | 2022-07-28 | 2022-09-16
128 | Design te prepare content | 2022-08-01 | 2022-08-12 | 125
129 | Draft content (v1) -- Exple corridors | 2022-07-28 | 2022-08-10 | 116,125
130 | ST Review draft content | 2022-08-11 | 2022-08-17 | 129
131 | Update content (v2) ---- Linked to design, and TAG | 2022-08-22 | 2022-09-02 | 130,128,126
132 | ST Final review for updated content | 2022-09-05 | 2022-09-09 | 131
133 | Finalize content/language | 2022-09-12 | 2022-09-16 | 132
134 | Build beta site | 2022-09-19 | 2022-10-10
135 | Build beta site | 2022-09-19 | 2022-09-23 | 133
136 | ST review beta site | 2022-09-26 | 2022-09-30 | 135
137 | Update beta site | 2022-10-03 | 2022-10-05 | 136
138 | ST final review beta site | 2022-10-06 | 2022-10-10 | 137
139 | Pencils down/final develoent | 2022-10-11 | 2022-11-07
140 | Transcreation (beta site and maps) | 2022-10-11 | 2022-10-19 | 138
141 | Build translated beta sites | 2022-10-20 | 2022-10-27 | 140
142 | In-language QC of beta sites | 2022-10-28 | 2022-11-01 | 141
143 | Final edits/ST approval to launch | 2022-11-02 | 2022-11-07 | 142
144 | OOH is live | 2022-11-09 | 2022-12-05 | 143
145 | Summarize OOH themes, action items | 2022-12-06 | 2022-12-19 | 144
146 | Themes available for TAG (12/7, 1/4) | 2022-12-19 | 2022-12-19 | 145
147 | General outreach prep and conduct (round 2) | 2023-09-05 | 2023-12-13 | 116,144
148 | Draft content | 2023-09-05 | 2023-09-13 |  | Remove linkage to design (was tied to 249)
149 | ST Review draft content | 2023-09-14 | 2023-09-20 | 148
150 | ST approve site frework | 2023-09-21 | 2023-09-27 | 149
151 | Update content and graphics (dev build shell) | 2023-09-28 | 2023-10-04 | 150
152 | ST content review (Chelsea) | 2023-10-05 | 2023-10-11 | 151
153 | Finalize content | 2023-10-12 | 2023-10-18 | 152
154 | ST beta review | 2023-10-19 | 2023-10-25 | 153
155 | Translation/Build beta site/finalize | 2023-10-26 | 2023-11-08 | 154
156 | OOH is live | 2023-11-09 | 2023-11-29 | 155
157 | Summarize OOH themes, action items | 2023-11-30 | 2023-12-13 | 156
158 | 3.5 Workshops, Drop-ins and Tabling | 2022-05-02 | 2023-09-29 | 1
159 | 3.6 Outreach to Underserved Communities | 2022-05-02 | 2023-09-29 | 1
160 | 3.7 Develop Support Graphics | 2022-05-02 | 2023-09-29 | 1
161 | 3.8 Engagement Summary | 2022-12-06 | 2024-02-07
162 | Round 1 Summary Doc | 2022-12-06 | 2023-01-30
163 | Draft Round 1 Summary | 2022-12-06 | 2022-12-19 | 144
164 | QAQC Round 1 Summary | 2022-12-20 | 2022-12-26 | 163
165 | ST review Round 1 Summary | 2022-12-27 | 2023-01-09 | 164
166 | Final Round 1 Summary | 2023-01-10 | 2023-01-23 | 165
167 | QAQC Final Round 1 Summary | 2023-01-24 | 2023-01-30 | 166
168 | Submit Final Round 1 Summary | 2023-01-30 | 2023-01-30 | 167
169 | Round 2 Summary Doc | 2023-12-14 | 2024-02-07
170 | Draft Round 2 Summary | 2023-12-14 | 2023-12-27 | 157
171 | QAQC Round 2 Summary | 2023-12-28 | 2024-01-03 | 170
172 | ST review Round 2 Summary | 2024-01-04 | 2024-01-17 | 171
173 | Final Round 2 Summary | 2024-01-18 | 2024-01-31 | 172
174 | QAQC Final Round 2 Summary | 2024-02-01 | 2024-02-07 | 173
175 | Submit Final Round 2 Summary | 2024-02-07 | 2024-02-07 | 174
176 | Project Engagement Summary Doc | 2023-01-31 | 2023-04-10 |  | Delete task as is completed w/ OOH docs above (2 docs)
177 | Draft Engagement Summary | 2023-01-31 | 2023-02-27 | 168
178 | QAQC Draft Engagement Summary | 2023-02-28 | 2023-03-06 | 177
179 | ST review Draft Engagement Summary | 2023-03-07 | 2023-03-20 | 178
180 | Final Engagement Summary | 2023-03-21 | 2023-04-03 | 179
181 | QAQC Final Engagement Summary | 2023-04-04 | 2023-04-10 | 180
182 | Submit Final Engagement Summary | 2023-04-10 | 2023-04-10 | 181
183 | 3.9 City Council Briefings | 2022-05-02 | 2023-09-29 | 1
184 | 4 Conceptual Engineering | 2022-05-02 | 2023-12-29
185 | 4.1 Design Standards | 2022-05-02 | 2022-07-01
186 | Draft Design Criteria and Standards | 2022-05-02 | 2022-06-03 | 1
187 | QAQC Draft Design Criteria and Standards | 2022-06-06 | 2022-06-10 | 186
188 | ST and City review Draft Design Criteria and Standards | 2022-06-13 | 2022-06-24 | 187
189 | Final Design Criteria and Standards | 2022-06-27 | 2022-06-30 | 188
190 | QAQC Final Design Criteria and Standards | 2022-07-01 | 2022-07-01 | 189
191 | Submit Final Design Criteria and Standards | 2022-07-01 | 2022-07-01 | 190
192 | 4.2 Design Kick-Off Meeting | 2022-06-15 | 2022-06-15 | 1 | Scheduled
193 | 4.3 Aerial Survey and Mapping | 2022-05-02 | 2022-09-22
194 | Set aerial control targets | 2022-05-02 | 2022-05-20 | 1
195 | Conduct aerial survey and mapping | 2022-05-23 | 2022-06-10 | 194
196 | Process survey data | 2022-06-13 | 2022-07-01 | 195
197 | Draft survey data for ST/AHJ review | 2022-07-04 | 2022-07-08 | 196
198 | ST/AHJ review draft survey data | 2022-07-11 | 2022-07-22 | 197
199 | Finalize survey data | 2022-09-16 | 2022-09-22 | 198 | Updated from 7/2022 to 9/22
200 | 4.4 Conceptual Engineering Drawings | 2022-06-27 | 2023-10-31
201 | Identify effects & constraints | 2022-06-27 | 2022-08-05
202 | Develop effects & constraints lists/maps | 2022-06-27 | 2022-07-08 | 119,188 | Disconnect from survey
203 | City review | 2022-07-11 | 2022-07-22 | 202
204 | Finalize alternative definitions based on effects & constraints - for outreach | 2022-07-25 | 2022-08-05 | 203
205 | Develop CE drawings | 2022-10-06 | 2023-10-31
206 | Final input from City - S Tyler, Washington-47th | 2023-04-20 08:00 | 2023-04-20 08:00
207 | Draft CE drawings | 2022-10-06 | 2023-05-31 | 204,199,206FF+30d | Driven by 4/20 meeting w/ Tacoma + 2 months of design
208 | QAQC draft CE drawings | 2023-06-01 | 2023-06-21 | 207 | Change to 15 days - quick turn around
209 | ST and City review draft CE drawings | 2023-06-22 | 2023-09-12 | 208 | Bump out date for South Tacoma review (+2 weeks plus TAG 9/12)
210 | Finalize CE drawings | 2023-09-13 | 2023-10-17 | 209 | Reduce from 30 to 25, to account for extended Draft period; Add Kirk to te to draft CE
211 | QAQC final CE drawings | 2023-10-18 | 2023-10-31 | 210
212 | 4.5 Conceptual Stormwater Design | 2022-05-02 08:00 | 2023-11-14
213 | Collect and review available stormwater data | 2022-05-02 08:00 | 2022-07-22 | 1
214 | Determine USGS soil types for each project site/LID feasibility | 2022-05-02 08:00 | 2022-07-22 | 1
215 | Identify and document stormwater code | 2022-05-02 | 2022-07-22 | 1
216 | Concept Stormwater Design | 2023-06-01 | 2023-11-14
217 | Draft Stormwater design | 2023-06-01 | 2023-06-14 | 188,213,214,215,207
218 | QAQC draft Stormwater design | 2023-06-15 | 2023-06-28 | 217
219 | ST review draft Stormwater design | 2023-06-29 | 2023-07-12 | 218,259 | Tied to CE doc 1 submittal
220 | Finalize Stormwater design | 2023-10-18 | 2023-10-31 | 210 | Reduced duration to align w/ final CE report
221 | QAQC final Stormwater design | 2023-11-01 | 2023-11-14 | 220 | Reduced duration to align w/ final CE report
222 | 4.6 Concept Utl Relocation | 2022-05-02 | 2023-11-14
223 | Utility request letter/as-built request | 2022-05-02 | 2022-06-10 | 1
224 | Utility ITS/traffic signal as-built request | 2022-05-02 | 2022-06-10 | 1
225 | Utility research | 2022-05-02 | 2022-06-10 | 1
226 | City/Utilities gather data and submit | 2022-06-13 | 2022-07-11 | 223,224,225
227 | Concept Utl Relocation | 2023-06-01 | 2023-11-14
228 | Draft utility matrix | 2023-06-01 | 2023-06-14 | 188,226,207 | Tied to CE
229 | Draft conceptual utility relocation | 2023-06-01 | 2023-06-14 | 188,226,207 | Tied to CE
230 | QAQC draft conceptual utility relocation | 2023-06-15 | 2023-06-28 | 229,228
231 | ST review draft conceptual utility relocation | 2023-06-29 | 2023-07-12 | 230,258 | Tied to CE doc 1 submittal
232 | Finalize conceptual utility relocation | 2023-10-18 | 2023-10-31 | 210 | Reduced duration to align w/ final CE report
233 | QAQC final conceptual utility relocation | 2023-11-01 | 2023-11-14 | 232 | Reduced duration to align w/ final CE report
234 | Stormwater/ROW info to Env | 2023-06-14 | 2023-06-14 | 229,217 | New coordination task - design to env, cost estimating
235 | 4.8 Capital Construction Cost Estimating | 2022-10-03 | 2023-12-29
236 | Cost Estimating kick off meeting | 2022-10-03 | 2022-10-03 | 1
237 | Methodology report | 2022-10-04 | 2023-01-11
238 | Draft Capital Construction Cost methodology | 2022-10-04 | 2022-12-07 | 236
239 | QAQC draft Capital Construction Cost methodology | 2022-12-08 | 2022-12-14 | 238
240 | ST review draft Capital Construction Cost methodology | 2022-12-15 | 2022-12-28 | 239
241 | Finalize Capital Construction Cost methodology | 2022-12-29 | 2023-01-04 | 240
242 | QAQC final Capital Construction Cost methodology | 2023-01-05 | 2023-01-11 | 241
243 | Submit final Capital Construction Cost methodology | 2023-01-11 | 2023-01-11 | 242
244 | Capital construction cost estimate | 2023-07-11 | 2023-12-29
245 | Develop working/draft CCE | 2023-07-11 | 2023-07-19
246 | Share working/draft CCE with ST for T/TAG prep | 2023-07-20 | 2023-07-26 | 245
247 | T, and Tacoma TAG | 2023-07-27 | 2023-08-02 | 246
248 | Draft CCE | 2023-11-01 | 2023-11-09 | 210,220,232 | tie to resolve Tacoma comments, Draft CE
249 | QC CCE (DEA/X) | 2023-11-10 08:00 | 2023-11-16 | 248 | May occur during/before the Draft CCCE
250 | QC CCE (Ott Sakai) | 2023-11-22 08:00 | 2023-11-28 | 249
251 | QA CCE | 2023-11-29 08:00 | 2023-12-01 | 250 | Pushes outreach out
252 | ST review CCE | 2023-12-04 08:00 | 2023-12-15 | 251
253 | Finalize CCE | 2023-12-18 08:00 | 2023-12-22 | 252
254 | QAQC CCE | 2023-12-25 08:00 | 2023-12-29 | 253
255 | Submit final CCE | 2023-12-29 | 2023-12-29 | 254
256 | 4.9 Conceptual Engineering Report | 2022-05-02 08:00 | 2023-12-29
257 | Draft CE Report | 2022-05-02 08:00 | 2022-05-27
258 | QAQC Draft CE Report | 2022-05-02 08:00 | 2022-05-13
259 | Submit Draft CE Report | 2023-06-21 | 2023-06-21 | 208
260 | ST review Draft CE Report | 2023-06-22 08:00 | 2023-09-12 | 259
261 | Finalize CE Report | 2023-11-15 08:00 | 2023-11-28 | 233,221
262 | QAQC Final CE Report | 2023-11-29 08:00 | 2023-12-12 | 261
263 | Submit Final CE Report (includes final CE, stormwater, utility, CCE) | 2023-12-29 | 2023-12-29 | 262,233,221,211,255
264 | 5 Implementation Plan | 2022-05-02 08:00 | 2023-09-15
265 | 5.1 Project Workshops | 2022-05-02 08:00 | 2022-08-23
266 | Prep for workshop #1 | 2022-05-02 08:00 | 2022-05-27 | 1
267 | Workshop #1 | 2022-05-30 08:00 | 2022-05-30 | 266
268 | Prep for workshop #2 | 2022-05-31 08:00 | 2022-08-22 | 267
269 | Workshop #2 | 2022-08-23 08:00 | 2022-08-23 | 268
270 | 5.2 Document Sound Transit and Partner Agency Roles and Responsibilities | 2022-05-02 08:00 | 2023-09-01 | 1
271 | 5.3 Implementation Plan | 2023-09-04 08:00 | 2023-09-15 | 270

## Resource_Table
ID | Type | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes

## Assignment_Table
Task Name | Work